AZURE PROJECT EXECUTION PLAN

VERSION 2.0

GraphRAG + ReAct Agent + LangChain Integration

Structuring Unstructured Expert Knowledge

Author: Muhammad Rafiq

KU Leuven - Advanced Master in AI in Business and Industry

February 2026

# Executive Summary

This project plan incorporates three advanced RAG technologies aligned with the thesis research:

- GraphRAG: Knowledge graph with hierarchical community summaries (thesis Section 2.9)

- ReAct Agent: Multi-step reasoning with verification (thesis Section 2.8, Yao et al.)

- LangChain/LangGraph: Orchestration framework throughout the pipeline

Timeline: 22 weeks (extended from 20 to accommodate GraphRAG and ReAct phases)

# 1. Phase Overview (22 Weeks)

| Phase | Name | Weeks | Key Deliverables |
| --- | --- | --- | --- |
| P1 | Azure Environment & LangChain Setup | 1-2 | Infrastructure, LangChain project |
| P2 | Data Ingestion | 3-5 | LangChain loaders, Bronze zone |
| P3 | NLP Processing | 6-8 | Chunking, NER, anonymization |
| P4 | Vector Index & Basic RAG | 9-10 | AI Search index, basic RAG chain |
| P5 | GraphRAG Construction | 11-14 | Graph, communities, summaries |
| P6 | ReAct Agent Development | 15-17 | Tools, agent, query router |
| P7 | Integration & Evaluation | 18-20 | RAGAS metrics, comparison |
| P8 | Hardening & Documentation | 21-22 | Security, thesis chapters |

## 1.1 Gantt Chart

Week:  1  2  3  4  5  6  7  8  9 10 11 12 13 14 15 16 17 18 19 20 21 22

─────────────────────────────────────────────────────────────────

P1     ██████

P2           ████████████

P3                       ████████████

P4                                   ████████

P5                                           ████████████████

P6                                                           ████████████

P7                                                                   ████████

P8                                                                       ████████

─────────────────────────────────────────────────────────────────

M1▲       M2▲        M3▲    M4▲        M5▲          M6▲    M7▲  M8▲

# 2. Phase 5: GraphRAG Construction (Weeks 11-14)

| Attribute | Detail |
| --- | --- |
| Objective | Build knowledge graph with hierarchical community structure |
| Challenges | C1 (Conflicting Info), C5 (Semantic Similarity), C7 (Hallucination) |
| Technologies | Cosmos DB Gremlin, igraph, leidenalg, GPT-4o, LangChain |

Weekly Activities:

- Week 11: Entity & relationship extraction using GPT-4o with Pydantic structured outputs

- Week 12: Cosmos DB Gremlin setup; graph population with entity deduplication

- Week 13: Leiden algorithm community detection at multiple resolutions (0.5, 1.0, 2.0)

- Week 14: Community summarization using GPT-4o; index summaries in AI Search

Deliverables:

- D5.1: Entity extraction pipeline (GPT-4o + Pydantic)

- D5.2: Knowledge graph (Cosmos DB Gremlin, >10K nodes)

- D5.3: Community hierarchy (3 levels, >95% coverage)

- D5.4: Community summaries index (Azure AI Search)

# 3. Phase 6: ReAct Agent Development (Weeks 15-17)

| Attribute | Detail |
| --- | --- |
| Objective | Implement ReAct agent with multi-step reasoning and verification |
| Thesis Reference | Section 2.8: Yao et al. ReAct for hallucination mitigation |
| Technologies | LangGraph, Azure OpenAI GPT-4o, custom tools |

Weekly Activities:

- Week 15: Implement tools: vector_search, graph_traverse, community_search, glossary_lookup, verify_fact

- Week 16: Create LangGraph ReAct agent; configure system prompt; implement memory

- Week 17: Build query router (local/entity/global/complex); integrate with all retrieval methods

Deliverables:

- D6.1: ReAct tool suite (5 tools, <2s latency each)

- D6.2: LangGraph ReAct agent (2-4 reasoning steps avg)

- D6.3: Query router (>85% correct routing)

- D6.4: Verification system (verify_fact tool)

# 4. Milestones

| Milestone | Week | Criteria |
| --- | --- | --- |
| M1: Environment Ready | 2 | Azure deployed; LangChain chain executes |
| M2: Ingestion Complete | 5 | >99% files in Bronze zone |
| M3: NLP Pipeline Ready | 8 | PII recall >95%; Silver zone populated |
| M4: Basic RAG Operational | 10 | Baseline MRR measured |
| M5: GraphRAG Complete | 14 | >10K graph nodes; communities detected |
| M6: ReAct Agent Ready | 17 | Agent answers queries with verification |
| M7: Evaluation Complete | 20 | All success criteria measured |
| M8: Project Complete | 22 | Production system; thesis ready |

# 5. Updated Success Criteria

| Metric | Target | Measurement |
| --- | --- | --- |
| Document Processing | >95% coverage | Processing logs |
| PII Detection Recall | >95% | Annotated test set |
| Graph Entity Coverage | >90% key entities | Entity audit |
| Community Quality | Modularity >0.4 | Leiden metrics |
| Global Query Accuracy | >75% | Synthesis test set |
| Self-Correction Rate | >20% | ReAct trace analysis |
| Hallucination Reduction | >30% vs baseline | A/B comparison |
| Retrieval MRR@10 | >0.70 | RAGAS evaluation |
| Answer Faithfulness | >0.88 | RAGAS evaluation |

# 6. Comparative Evaluation Design

| Configuration | Components | Purpose |
| --- | --- | --- |
| Baseline | Vector search only | Traditional RAG baseline |
| +GraphRAG | Baseline + Graph + Communities | Demonstrate GraphRAG value |
| +ReAct | Baseline + ReAct Agent | Demonstrate ReAct value |
| Full System | Vector + GraphRAG + ReAct | Complete integrated system |

# 7. Updated Budget Estimate

| Service | Monthly EUR | Notes |
| --- | --- | --- |
| Azure OpenAI (GPT-4o) | 350-600 | Extraction + summaries + agent |
| Azure OpenAI (Embeddings) | 50-100 | Chunk embeddings |
| Azure AI Search (S1) | 200-300 | Vector + community indexes |
| Cosmos DB (Gremlin) | 100-200 | Graph storage |
| AKS | 200-400 | Microservices |
| Other | 100-200 | Storage, networking, monitoring |
| TOTAL | 1,000-1,800 | Development phase |

--- End of Project Plan v2.0 ---