PROJECT EXECUTION PLAN

Structuring Unstructured Expert Knowledge

GraphRAG + ReAct + LangChain | 11-Week Accelerated Timeline

# 1. Project Overview

Build an AI-powered knowledge system processing 10-15GB of enterprise documents (PST, PDF, DOCX, XLSX) with GraphRAG for global queries, ReAct agent for verified retrieval, and LangChain orchestration.

⚠ Key Constraint: Week 2 Presentation - Must demonstrate working ingestion pipeline with initial results.

# 2. Phase Overview

| Phase | Name | Weeks | Key Outcome |
| --- | --- | --- | --- |
| P1 | Setup & Ingestion | 1-2 | Azure deployed; data ingested; DEMO READY |
| P2 | NLP Processing | 3-4 | Chunks, NER, anonymization complete |
| P3 | Vector Index | 5 | Basic RAG operational; baseline metrics |
| P4 | GraphRAG | 6-8 | Knowledge graph with community summaries |
| P5 | ReAct Agent | 9-10 | Multi-step reasoning with verification |
| P6 | Evaluation | 11 | RAGAS metrics; thesis documentation |

# 3. System Architecture (Editable)

Note: This diagram is built with Word tables - click any box to edit text, colors, or layout.

DATA SOURCES

PST/MSG; PDF; DOCX; XLSX; PPTX.

↓

INGESTION LAYER (LangChain Loaders)

Document Loaders → Text Extraction → Metadata → Bronze Zone (ADLS Gen2)

↓

NLP PROCESSING LAYER

Chunking; NER (spaCy); Anonymization; Summarization.

↓

KNOWLEDGE STORES

Vector Index (Azure AI Search); Knowledge Graph (Cosmos DB Gremlin).

↓

GRAPHRAG LAYER

Entity Extraction (GPT-4o); Community Detection (Leiden); Community Summaries (GPT-4o).

↓

ReAct AGENT LAYER (LangGraph)

Query → [THINK → ACT → OBSERVE]* → Verify → Answer Tools: vector_search ¦ graph_traverse ¦ community_search ¦ verify_fact

# 4. Weekly Task Breakdown

## Week 1: Azure Setup & Initial Ingestion

- Deploy Azure: Resource Group, VNet, Key Vault, ADLS Gen2, Cosmos DB, Azure OpenAI

- Configure GPT-4o and text-embedding-3-large deployments

- Set up Python project with LangChain dependencies

- Build PST/MSG loader (libpst); configure PDF, DOCX, XLSX loaders

- Start processing PST archives (email extraction, threading)

Output: Azure environment; loaders operational

## Week 2: Complete Ingestion + PRESENTATION DEMO

- Complete all document ingestion (Bronze zone populated)

- Implement language detection (EN/NL)

- Build basic chunking pipeline (RecursiveCharacterTextSplitter)

- Create simple RAG demo with sample documents

- Prepare presentation slides showing architecture + working pipeline

🎯 MILESTONE M1: Presentation demo - show ingestion pipeline, sample retrieval

## Week 3: Semantic Chunking & NER

- Implement LangChain SemanticChunker with Azure embeddings

- Configure spaCy NER models (en_core_web_trf, nl_core_news_lg)

- Build entity extraction pipeline with normalization

- Create domain glossary from extracted entities

Output: Semantic chunks; NER pipeline operational

## Week 4: Anonymization & Summarization

- Configure Presidio with Belgian PII patterns

- Implement pseudonymization with mapping store

- Build GPT-4o summarization chain (chunk → document)

- Populate Silver zone with processed data

MILESTONE M2: NLP complete; PII recall >95%

## Week 5: Vector Index & Basic RAG

- Configure Azure AI Search (HNSW, 3072 dims, hybrid search)

- Index all chunks with embeddings

- Implement LangChain RAG chain

- Measure baseline metrics (MRR, NDCG)

MILESTONE M3: Basic RAG operational; baseline recorded

## Weeks 6-8: GraphRAG Construction

Week 6 - Entity Extraction:

- GPT-4o extraction with Pydantic structured outputs

- Entity types: PERSON, ORG, PROJECT, TECHNOLOGY; relationship extraction

Week 7 - Knowledge Graph:

- Configure Cosmos DB Gremlin; implement graph storage

- Process all chunks; populate graph (>10K nodes)

Week 8 - Communities:

- Leiden algorithm (resolutions: 0.5, 1.0, 2.0)

- Generate and index community summaries

MILESTONE M4: GraphRAG complete; communities summarized

## Weeks 9-10: ReAct Agent Development

Week 9 - Tools:

- Implement: vector_search, graph_traverse, community_search, glossary_lookup, verify_fact

Week 10 - Agent:

- LangGraph ReAct agent with query router

- Integrate all retrieval methods

MILESTONE M5: ReAct agent operational

## Week 11: Evaluation & Documentation

- RAGAS evaluation (faithfulness, relevancy, precision, recall)

- Comparative analysis: Baseline vs +GraphRAG vs +ReAct vs Full

- Complete thesis methodology and results chapters

MILESTONE M6: All success criteria validated

# 5. Milestones & Success Criteria

| Milestone | Week | Deliverables | Success Criteria |
| --- | --- | --- | --- |
| M1 🎯 | 2 | Presentation demo | Working ingestion + basic retrieval demo |
| M2 | 4 | NLP pipeline complete | PII recall >95%; Silver zone populated |
| M3 | 5 | Basic RAG | Baseline MRR measured |
| M4 | 8 | GraphRAG complete | >10K graph nodes; summaries indexed |
| M5 | 10 | ReAct agent | Agent with verification working |
| M6 | 11 | Final evaluation | MRR >0.70; Faithfulness >0.85 |

## 5.1 Key Metrics

| Category | Metric | Target |
| --- | --- | --- |
| Processing | Document coverage | >95% |
| Privacy | PII detection recall | >95% |
| GraphRAG | Entity coverage | >90% |
| GraphRAG | Global query accuracy | >75% |
| ReAct | Hallucination reduction | >30% vs baseline |
| Overall | MRR@10 | >0.70 |
| Overall | Answer faithfulness | >0.85 |

# 6. Comparative Evaluation

| Config | Components | Purpose |
| --- | --- | --- |
| Baseline | Vector search only | Traditional RAG baseline |
| +GraphRAG | Baseline + Graph + Communities | GraphRAG contribution |
| +ReAct | Baseline + ReAct Agent | ReAct contribution |
| Full | Vector + GraphRAG + ReAct | Complete system |

# 7. Deliverables Checklist

| Wk | Deliverable |
| --- | --- |
| 1 | Azure infrastructure (Terraform) |
| 1 | LangChain document loaders |
| 2 | Bronze zone with all data + PRESENTATION |
| 3 | Semantic chunking service |
| 3 | NER pipeline (EN/NL) |
| 4 | Anonymization pipeline |
| 4 | Silver zone |
| 5 | Azure AI Search index |
| 5 | Basic RAG chain |
| 6 | Entity extraction pipeline |
| 7 | Knowledge graph (Cosmos DB) |
| 8 | Community hierarchy + summaries |
| 9 | ReAct tool suite (5 tools) |
| 10 | LangGraph agent + query router |
| 11 | RAGAS report + thesis chapters |

See attached Excel file for editable Gantt chart