## Gantt Chart
PROJECT GANTT CHART - 11 Week Execution Plan
Structuring Unstructured Expert Knowledge ¦ GraphRAG + ReAct + LangChain
Phase | Task | Owner | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | Notes
P1 | Deploy Azure infrastructure | Dev | Planned | [11 empty] | VNet, KV, ADLS, Cosmos
P1 | Configure Azure OpenAI | Dev | Planned | [11 empty] | GPT-4o, embeddings
P1 | Setup LangChain project | Dev | Planned | [11 empty] | Dependencies
P1 | Build document loaders (PST, PDF, DOCX) | Dev | Planned | [11 empty] | All formats
P1 | Data ingestion to Bronze zone | Dev | Planned
P1 | Language detection | Dev | Planned | [11 empty] | EN/NL
P1 | Basic chunking for demo | Dev | Planned
P1 | Simple RAG demo | Dev | Planned | [11 empty] | Sample queries
P1 | Prepare presentation | Author | Planned |  | 🎯 | [9 empty] | Slides + demo
| ★ M1: PRESENTATION |  | MILESTONE |  | ◆ | [9 empty] | DEMO INGESTION + RAG
P2 | Implement SemanticChunker | Dev | Planned | [11 empty] | LangChain
P2 | Configure spaCy NER (EN/NL) | Dev | Planned
P2 | Entity extraction pipeline | Dev | Planned
P2 | Create domain glossary | Dev | Planned
P2 | Configure Presidio anonymization | Dev | Planned | [11 empty] | Belgian patterns
P2 | Summarization chain (GPT-4o) | Dev | Planned
P2 | Populate Silver zone | Dev | Planned
| ★ M2: NLP Complete |  | MILESTONE |  |  |  | ◆ | [7 empty] | PII recall >95%
P3 | Configure Azure AI Search | Dev | Planned | [11 empty] | HNSW, 3072 dims
P3 | Index chunks with embeddings | Dev | Planned
P3 | LangChain RAG chain | Dev | Planned
P3 | Baseline metrics (MRR, NDCG) | Dev | Planned
| ★ M3: Basic RAG |  | MILESTONE |  |  |  |  | ◆ | [6 empty] | Baseline recorded
P4 | Entity extraction (GPT-4o + Pydantic) | Dev | Planned | [11 empty] | Structured outputs
P4 | Define entity/relationship types | Dev | Planned
P4 | Configure Cosmos DB Gremlin | Dev | Planned
P4 | Populate knowledge graph | Dev | Planned | [11 empty] | >10K nodes
P4 | Entity resolution | Dev | Planned | [11 empty] | Deduplication
P4 | Leiden community detection | Dev | Planned | [11 empty] | igraph + leidenalg
P4 | Community summaries (GPT-4o) | Dev | Planned | [11 empty] | Hierarchical
P4 | Index summaries in AI Search | Dev | Planned
| ★ M4: GraphRAG Complete |  | MILESTONE | [7 empty] | ◆ |  |  |  | Communities indexed
P5 | Tool: vector_search | Dev | Planned
P5 | Tool: graph_traverse | Dev | Planned
P5 | Tool: community_search | Dev | Planned
P5 | Tool: verify_fact | Dev | Planned
P5 | LangGraph ReAct agent | Dev | Planned
P5 | Query router (StateGraph) | Dev | Planned
P5 | Integration testing | Dev | Planned
| ★ M5: ReAct Agent Ready |  | MILESTONE | [9 empty] | ◆ |  | Verification working
P6 | RAGAS evaluation | Dev | Planned | [11 empty] | All metrics
P6 | Comparative analysis (4 configs) | Author | Planned
P6 | Thesis chapters | Author | Planned | [11 empty] | Methods, Results
P6 | Reproducibility package | Dev | Planned | [11 empty] | IaC, configs
| ★ M6: PROJECT COMPLETE |  | MILESTONE | [10 empty] | ◆ | All validated
LEGEND:
P1: Setup & Ingestion |  |  |  |  | P2: NLP Processing |  |  |  |  | P3: Vector Index
P4: GraphRAG |  |  |  |  | P5: ReAct Agent |  |  |  |  | P6: Evaluation
◆ Milestone |  |  |  |  | 🎯 Presentation (Week 2)